## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## PROJECT SCHEDULE
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Client-Server Based UTM Onboarding System
NAME | VEDANT PATIL
INTERN ID | IP -6748
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
| 1 Requirement Analysis |  |  |  |  | COMPLETED
1.1 Understand the CA onboarding workflow
1.2 Identify required input fields (Name, Email)
1.3 Define structure of the UTM link and email content
| 2 Design Phase |  |  |  |  | COMPLETED
2.1 Design the client-server architecture
2.2 Plan email integration using JavaMail API
| 3 Development Phase |  |  |  |  | COMPLETED
3.1 Implement the Client Module to collect and send Name and Email to server
3.2 Implement the Server Module to receive data and generate UTM link
3.3 Integrate EmailSender class to send welcome email with UTM link
3.4 Format email message and apply basic error handling
| 4 Testing & Validation |  |  |  |  | COMPLETED
4.1 Test socket communication between client and server
4.2 Test UTM link creation with different names (check formatting)
4.3 Validate email delivery using test Gmail account
| 5 Deployment & Handover |  |  |  |  | COMPLETED
5.1 Clean and organize project files (Client.java, Server.java, EmailSender.java)