## TEST PLAN
TEST PLAN
PROJECT NAME | Client-Server Based UTM Onboarding System
PROJECT ID | Intern ID: IP6748
INTERN NAME | Vedant Patil
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
This test plan outlines the testing strategy and approach for verifying the functionality of the CA Onboarding Automation System. The system automates UTM link generation and dispatches it via email to newly registered users.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Client inputs (name, email) Server receives data and creates UTM link EmailSender sends email with UTM link
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
UI-based form submission
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
Ensure accurate UTM link generation Verify email delivery with correct content Validate client-server communication Handle invalid or missing input gracefully
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
NA
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
the focus is on testing the functionality of the system (UTM generation and email sending) without needing to look at the internal code. This approach helps us ensure that the user inputs are correctly handled, UTM links are generated as expected, and emails are successfully sent—matching real-world usage.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
1. Unit Testing – Test each part separately (like UTM link creation, email sending). 2. Integration Testing – Check if parts work well together (client input → server → email sending). 3. System Testing – Test the whole system to see if it works end-to-end. 4. Acceptance Testing – Make sure the system does what the user expects (like sending the UTM link after form submission).
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
100% test coverage All Manual & Automated Test cases executed All open bugs are fixed or will be fixed in next release
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Plan – Describes how testing will be done. Test Cases – Steps to check if the system works correctly. Test Data – Sample inputs used for testing. Test Report – Summary of test results (pass/fail). Bug Report – List of problems found during testing. Final Test Summary – Overall status after all tests are done.
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
VS code, Mannual testing
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
IDE: Visual Studio Code (VS Code) Programming Language: Java (JDK 11 or higher) Build & Run: Manual and execution via VS Code terminal Libraries: JavaMail API (for email functionality) Java IO and Networking (for socket communication) Operating System: Windows 11
ADDITIONAL COMMENTS
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Client Input Handling | Check if the client correctly takes user name and email as input. |  |  |  | PASSED
Server Connection |  |  |  |  | PASSED
Email Sending | check whether the email is successfully sent or not |  |  |  | PASSED
Exception Handling | Validate how the system behaves if wrong input is given or network fails. |  |  |  | PASSED
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.